## Requirements
Functional Requirements:
| Name | Current Status: | Needed Before Launch: | Wanted Before Launch: | Estimated Hours Needed: |  | Status Options: | Description:
1 | Player Can move around in the world | Functional |  | Animation (partially done) and playtesting with new terrain |  |  | Perfect | There's nothing to improve upon.
2 | Dialogue System | Very Scuffed | Technically it works, but it hasn't been implemented yet beyond a simple test | Updated UI for the dialogue so it fits within the artstyle of the game | 4 to Functional | 4 | Done | It's intuitive to the user, it's robust, and works as intended.
3 | Quests | DNE Yet |  |  | 3 to Scuffed, 5 after that to Functional | 8 | Functional | It's not polished at all, it definitely SHOULD be improved before launch, but it does functionally work as intended.
4 | Special Object Interaction | Very Scuffed | An interaction system technically exists with the dialogue system, but it hasn't been fully implemented yet. |  | 10 to Functional | 10 | Very Scuffed | The system is somewhat in place, it works when only used as intended, but it may not be intuitive or it has some bugs to work out.
5 | Minigame | DNE Yet |  |  | 20 to Functional | 20 | Totally Broken | The system exists, but it doesn't function as intended in the slightest.
6 | Menu Screen | DNE Yet |  |  | 4 to Functional | 4 | DNE Yet | I need to get hustling
Other:
7 | Animation (in general) | 20% | Talk animations for all characters, interact animation for PC | Walking animations for all NPCs, variations on talking animations for all characters | *cries* | 20
8 | 3D Models (in general) | 20% | More character models for NPCs, and models for the environment (houses, trees, etc.) |  | Probably 16 hours to get all the basic environment models + NPC models done | 16
9 | Dialogue Writing/VAing | 40% | Lines are partially written, they just need to be finished according to the outline and then put in the proper format for the dialogue engine. | Some extra little dialogue lines for extra characters if you go out of your way to interact with them. | 7 hours to complete + format | 7
10 | Sound Effects | 0% | Any interaction needs a sound effect. Something I can either find for free online or put a random sound into Audacity and put it through filters until it sounds right | There'll be a basic sound for the "interaction" action, and for dialogue initiation. Every other sound effect will be considered polish for time reasons. | 1 hour to functional, 4 hours to find and put a good variety of sounds in. | 5
11 | Music | 40% | Technically I have quite a few songs worked out, but they're all in the form of rusty old practice room piano covers, so I need to take the melodies and make them in an actual music program. I currently have a music production workflow set up on my laptop, so it shouldn't be hard it'll just take a bit of time. |  | Probably about 5 hours to get a few songs done. | 5
Total Estimated Hours to a functional game: |  | 99

## Timeline
January 2026
SUNDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY
2025-12-28 | 2025-12-29 | 2025-12-30 | 2025-12-31 | 2026-01-01 | 2026-01-02 | 2026-01-03 |  | Hours Per Week: |  | 5 | to | 8
[8 empty] | Weeks: | 16 | 80 | to | 128 | Hours total
2026-01-04 | 2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08 | 2026-01-09 | 2026-01-10
2026-01-11 | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-17
2026-01-18 | 2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-24 | Week 1
2026-01-25 | 2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-31 | Week 2
February 2026
SUNDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY
2026-02-01 | 2026-02-02 | 2026-02-03 | 2026-02-04 | 2026-02-05 | 2026-02-06 | 2026-02-07 | Week 3
2026-02-08 | 2026-02-09 | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-13 | 2026-02-14 | Week 4
2026-02-15 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-20 | 2026-02-21 | Week 5 | Lent starts
2026-02-22 | 2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-27 | 2026-02-28 | Week 6 | Most likely Midterms, plan accordingly
March 2026
SUNDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY
2026-03-01 | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-07 | Week 7 | Spring Break! Celebrate my birthday, get my driver's license, and then do 7 hours of work on this project.
2026-03-08 | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-13 | 2026-03-14 | Week 8 | Send to friends + family + anyone I know for an initial playtest
2026-03-15 | 2026-03-16 | 2026-03-17 | 2026-03-18 | 2026-03-19 | 2026-03-20 | 2026-03-21 | Week 9
2026-03-22 | 2026-03-23 | 2026-03-24 | 2026-03-25 | 2026-03-26 | 2026-03-27 | 2026-03-28 | Week 10
2026-03-22: 2026-03-29; 2026-03-23: 2026-03-30; 2026-03-24: 2026-03-31 | Week 11
April 2026
SUNDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY
2026-03-29 | 2026-03-30 | 2026-03-31 | 2026-04-01 | 2026-04-02 | 2026-04-03 | 2026-04-04 | Week 11 | Easter break!
2026-04-05 | 2026-04-06 | 2026-04-07 | 2026-04-08 | 2026-04-09 | 2026-04-10 | 2026-04-11 | Week 12
2026-04-12 | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-18 | Week 13
2026-04-19 | 2026-04-20 | 2026-04-21 | 2026-04-22 | 2026-04-23 | 2026-04-24 | 2026-04-25 | Week 14
2026-04-26 | 2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-30 |  |  | Week 15
May 2026
SUNDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY
2026-04-26 | 2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-30 | 2026-05-01 | 2026-05-02 | Week 15
2026-05-03 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09
2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16
2026-05-17 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-23
2026-05-24 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-05-30
2026-05-31